## Pilot Testing Feedback
Issue | Date Reported | User | Category | Response/Action Item | Status
How secure is the data? Will any sensitive information be stored, such as my Social Security Number? | 2015-01-01 | Thomas, Jerry | Data Security / Privacy | Instruct user to view Privacy Policy, construct internal policy and documentation around sensitive information | Complete
Can we edit records that are entered by another person, but linked to our profiles? | 2015-01-01 | Roberts, Ann | Manual Data Entry | Review, discuss and determine if we want to enable editable user-reference | Under Review
What if I'm not sure which screen is most appropriate for a specific activity? Who should I contact? | 2015-01-01 | Richards, Naiobi | Contact Our HelpDesk | Explain when to contact Digital Measures versus the university Administrator | Complete
Rapid Reports seems to have slightly different functionality than Run Custom Reports, could you explain the differences between the tools? | 2015-01-01 | Johnson, Joe | Rapid Reports | Create training documentation explaining when and how Rapid Reports should be used, and how this tool differs from Run Custom Reports | Under Review
How are records ordered on the Summary screen? | 2015-01-01 | Jones, Sandra | Summary Screen | Insert instructional text on the summary screen explaining how records are ordered | Submitted
What data will be imported on my behalf, and how consistently will this be done? For example, when can I expect to see my courses in the database? Will the campus be publishing a schedule? | 2015-01-01 | McGroarty, Estelle | Non-Manual Data Entry | Create documentation outlining which data will be imported and tentative schedule; provide this documentation to faculty | Under Review
How do I export my citation data out of other source systems, such as Endnote or Mendeley? Is there a resource you can point me to? | 2015-01-01 | Nettleman, Mary | BibTeX Imports/Documentation | Create overview with links to documentation: BibTeX Imports, PubMed, and the Faculty/Staff Guide | Complete
What is the Research Currently in Progress screen intended to capture, and how does this differ from the other Scholarship/Research screens? | 2015-01-01 | Richards, Naiobi | Data Entry | Create training documentation explaining when and how this screen should be used | Under Review